## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 53.7 | 3 |  |  |  | 16 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-10-19 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-03 | 2016-10-05 | 2016-10-07 | 2016-10-10 | 2016-10-12 | 2016-10-14 | 2016-10-17 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | --Player Related things | [23 empty] | Assigned
6 | 2 | Car movement | WS |  | 4 | 0 | 3 |  | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | boost powerup for car | AP |  | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Player 2 Movment | AP |  | 2 | 0 | 2 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Car Projectiles | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Car Pickups - Mines, Boost | ALL |  | 5 | 0 | 5 |  | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 2 | [24 empty] | Can't Repro
12
13 | 1 | Score keeping | ALL |  | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3 | Game Timer | ALL |  | 1 | 1 | 1 |  | 1 | bar: 2016-10-03 to 2016-10-19
15 | 1 | Start Screen | ALL |  | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 3 | Game Over Screen | AP |  | 3 | 0 | 3 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17
18 | 2 | Level Related Items | ALL |  | 4 | 2 | 2 |  | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
19 | 1 | The level made | WS |  | 3 |  | 3 |  | 3 | 2016-10-03: 3; 2016-10-05: 3; 2016-10-07: 3
20 | 1 | Ball made with movement after being hit | WS |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21
22
23 | 1 | Implement game with xbox controllers | AP | WS | 2 | 0 | 2 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24
25 |  | AFTER GOLD SPIKE
26
27
28
29 |  | Main Menu Changes | AP |  | 1 |  | 1 |  | 1 | bar: 2016-10-03 to 2016-10-10
30 | 1 | Turret Smooth Movment - per goldspike feedback | WS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 2 | UI Change for boost and Mine | AP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1 | Collision and other minor changes - bullets now collide with everything except teammate | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 1 | 4 Player Mode | AP |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 2 | adding sounds | WS |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1 | Input Changes - make game work for mac and windows | AP | WS | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3 | Game value Tweaks (boost, speed, power, etc) | WS | AP | 4 | 0 | 4 |  | 4 | 4 | 4 |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | adding aesthetics - particle systems and color to goals | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1 | Changing boost to absolute value rather than additive | WS |  | 0.2 | 0 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | Ball Reset Timer | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 |  | Car Was not moving or colliding accurately | WS |  | 2 | 0 | 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
108 |  | Issue when mines planted right under car and car doesn't move | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
109 |  | Some sounds causing objects not to collide | WS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
110 |  | Car movement Rework - changed to using AddForce | WS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 16 | 16 | 14 | 12 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 53.7 | 53.7 | 46.9875 | 40.275 | 30.2063 | 23.4937 | 16.7812 | 6.7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7 | 43.7
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 30.2 | 22.2 | 21.2 | 13.2 | 9.2 | 8.2 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 15.5 | 13.5 | 11.5 | 9.5 | 9.5 | 4.5 | 4.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
217 |  |  | 3 | [5 empty] | 8 | 8 | 5 | 1 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Adam Psarouthakis | AP |  |  |  |  | AP | 17 | 13 | 10 | 8 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 |  | William Shellabarger | WS |  |  |  |  | WS | 29.7 | 27.7 | 23.7 | 14.7 | 14.7 | 8.2 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 13 | 9 | 8 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7 | 53.7
236

## Daily Scrum
Producer | 2016-10-19 |  | Team Members
Approved | Dates |  | Adam Psarouthakis | William Shellabarger |  | All
| 2016-10-03 | Mon | Done: Got player movement going Next: Boost and player 2 move Help: Nothing now | Done: Built Playing arena Next: Implement Ball and get collisions feeling smooth Help: Car movement | Talked about what the game is gunna look like and where to start for making the game
| 2016-10-04 | Tue | Done: boost pick and implmintaion finished and UI for boost Next: player two movment | Done: Nothing today Next: Implement Ball
| 2016-10-05 | Wed | Done: Implemented keyboard controls for testing reasons Next: Whitebox the level Help: — | Done: Implemented Ball, hav it's movement feel realistic Next: Add Turret/projectiles to Car Help: Xbox controller compatability/drivers for OSX
| 2016-10-06 | Thu | Done: Reworked movement and put in game over and start screen Next: More power ups!! | Done: Changed boost powerup to feel better Next: Rearrange UI, add turret/projectiles, get controller working with OSX
| 2016-10-07 | Fri | Done: Ball fixes, to respawn and score keeping Next: Start screen overhaul | Done: Nothing today Next: See last cell
| 2016-10-08 | Sat | Done: Nothing today Next: Start Screen overahul | Done: Overhauled Movement to work with physics, rearraned boost/UI, added turrets/projectiles to UFO's Next: Add Mines |  | Wrote R & A document
| 2016-10-09 | Sun | Done: Met and got the submit ready to go for the gold spike | Done: Met and got the submit ready to go for the gold spike
| 2016-10-10 | Mon | Done: Nothing today Next: Start Screen Change Again To add player movment | Done: Nothing Today Next: Respond to goldspike feedback
| 2016-10-11 | Tue | Done: Start Screen Next: Add 4 PLayer compatiblity | Done: Changed Turrets to rotate snappy with Right Stick Next: Change boost to be absolute effect rather than additive, change mines so you can't lay them directly underneath player
| 2016-10-12 | Wed | Done: 4 Player map and start screen update Next: Input changes for 4 player | Done: Changed boost to be absolute effect, other minor game value changes Next: Change mines so they can't be laid underneath player
| 2016-10-13 | Thu | Done: Input for 4 player Next: the rest of 4 Player controls and game | Done: Nothing Today Next: Implement sounds, aesthetics, juiciness,
| 2016-10-14 | Fri | Done: Nothing Today Next: Play test and such and 4 player controls | Done: Changed so Mines push player away when being laid so they don't cause undetermined behavior when activating Next: Aesthetics
| 2016-10-15 | Sat | Done: 4 Player controls worked out well and power ups sorted out as well Next: More Play test and tweaks | Done: Nothing Today
| 2016-10-16 | Sun | Done: tweaks to gameplay made Next: Refine main menu so all parts are working and all options working | Done: Added aesthetics to game including soudns, music Next: add ball timer and more aesthetics including particle systems
| 2016-10-17 | Mon | Done: Finished main menu, can now interact with all players Next: Ensure builds work for both windows and mac for submission | Done: added particle ssystems for explosion, bullet contact Added ball timer when goal is scored |  | Wrote Justification Document
| 2016-10-18 | Tue | Done: See All | Done: See All |  | Done: Playtested builds of game to ensure both builds work and there are no major bugs Next: Submit!!
| 2016-10-19 | Wed
| 2016-10-20 | Thu
| 2016-10-21 | Fri
| 2016-10-22 | Sat
| 2016-10-23 | Sun
| 2016-10-24 | Mon